# Barina Land Project

Development Workflow Model

# 1. The Big Picture

Building this system involves four layers of work that move in order:

Concept  →  Design  →  Build  →  Deploy

The Concept phase is complete. Each of the four delivery phases (Foundation, Community, Institutions, Commerce) goes through Design, Build, and Deploy before the next phase begins. This ensures the system is usable at every stage.

# 2. How Each Phase Moves

Every phase follows this sequence:

Phase Kickoff

Design Sprint — wireframes, user flows, and screens produced

Review and Sign-Off — client confirms before anything is built

Database First — schema written and tested

Backend and API — logic and data operations built

Frontend — screens connected to live data

Testing — functional and user testing

Deploy to Staging — real environment, not localhost

Client Sign-Off — client tests and approves

Deploy to Production — live to the world

Monitor and Patch — bugs fixed, feedback collected

Next Phase Kickoff

# 3. Work Breakdown by Role

| Stage | Client | Project Lead | Developer | Designer |
| --- | --- | --- | --- | --- |
| Phase kickoff | Confirm scope and priorities | Break into tasks | Review tech requirements | Begin wireframes |
| Design sprint | Review and approve screens | Coordinate feedback | Flag technical constraints | Deliver final designs |
| Database | Review data structure | Approve schema | Write and test schema | — |
| Backend | Review API endpoints list | QA logic | Build APIs | — |
| Frontend | Preview builds | Coordinate reviews | Build UI | Support with assets |
| Testing | Participate in UAT | Manage bug log | Fix issues | Fix UI inconsistencies |
| Staging deploy | Test as a real user | Sign off checklist | Deploy and monitor | — |
| Production deploy | Final approval | Coordinate launch | Deploy | — |
| Monitor and patch | Report issues | Triage and prioritize | Fix and release | — |

# 4. Task Organization

## Task Types

Feature — new functionality being built for the first time

Fix — something broken that needs correcting

Improvement — existing feature made better

Content — text, images, or data being added

Config — settings, environment, or infrastructure

## Task Status Flow

Backlog  →  To Do  →  In Progress  →  In Review  →  Done

Backlog — known but not yet scheduled

To Do — scheduled for the current sprint, not yet started

In Progress — actively being worked on

In Review — built, waiting for review or testing

Done — approved and merged

## Priority Levels

P1 Critical — blocks everything else, fixed immediately

P2 High — needed before the phase goes live

P3 Medium — important but not blocking

P4 Low — nice to have, scheduled when there is room

# 5. Sprint Structure

Work runs in two-week sprints. Each sprint has a clear goal tied to the current phase.

Day 1 — Sprint planning: tasks assigned, goals set

Days 2 to 9 — Active building

Day 10 — Internal review and testing

Day 11 — Fixes from review

Day 12 — Staging deploy and client testing

Day 13 — Client feedback addressed

Day 14 — Sprint close, retrospective, next sprint planned

Each sprint produces something real — a working screen, a working feature, or a live API. No sprint ends with nothing to show.

# 6. Decision-Making Flow

Not every decision needs client input. The following rules apply:

## Client is always consulted on:

Scope changes — something added to or removed from a phase

Design direction — layouts, flows, content

Priority shifts — swapping what goes into a sprint

Anything that affects members or the public

## Team decides independently on:

Which library or tool to use for a technical problem

Code architecture and folder structure

Database optimizations

Bug fixes that do not change visible behaviour

# 7. Communication Rhythm

| Touchpoint | Frequency | Format | Who |
| --- | --- | --- | --- |
| Progress update | Every 3 days | Short written summary | Project Lead to Client |
| Sprint review | Every 2 weeks | Live walkthrough of what was built | Full team and Client |
| Design review | Per design sprint | Share screens, client comments | Designer and Client |
| Bug report | As needed | Short note with screenshot | Developer to Project Lead, Client if P1 or P2 |
| Phase sign-off | End of each phase | Full walkthrough before going live | Client |

# 8. Environments

| Environment | Purpose | Who Accesses It |
| --- | --- | --- |
| Local | Developer machine, daily building and testing | Developers only |
| Staging | Shared test environment, mirrors production | Team and Client for reviews |
| Production | Live system with real members and real data | Everyone |

Nothing goes to production without staging sign-off from the client. No exceptions.

# 9. Version Control Flow

How code is managed so nothing breaks and nothing gets lost.

main branch — production, always stable, protected

staging branch — what the client tests, merged into main after sign-off

feature branches — one branch per feature, merged into staging when ready

## Rules:

No one pushes directly to main or staging

Every feature gets its own branch

Code is reviewed before merging

Every merge to main is tagged with a version number

# 10. Phase-by-Phase Sprint Schedule

## Phase 1 — Foundation

Sprint 1: Database schema, authentication, member registration

Sprint 2: Plot map and admin panel (land and finance roles)

Sprint 3: M-Pesa payments and receipt generation

Sprint 4: Public website and progress tracker

Staging review → Client sign-off → Launch Phase 1

## Phase 2 — Community

Sprint 5: Community hub — events, projects, forums

Sprint 6: Governance and voting, member referrals

Sprint 7: Flutterwave, Stripe, and diaspora payment flows

Sprint 8: Infrastructure module and contractor directory

Staging review → Client sign-off → Launch Phase 2

## Phase 3 — Institutions

Sprint 9: School — enrollment, fees, notice board

Sprint 10: Clinic — appointments, staff roster

Sprint 11: Farm produce and pre-orders, activity bookings

Sprint 12: Utilities billing and full reporting dashboard

Staging review → Client sign-off → Launch Phase 3

## Phase 4 — Commerce

Sprint 13: Supermarket — catalog, orders, delivery

Sprint 14: Restaurants and shops

Sprint 15: Commercial space rentals and community marketplace

Sprint 16: Full analytics and investor reporting suite

Staging review → Client sign-off → Launch Phase 4

# 11. Quality Checkpoints

Before anything moves to the next stage it must pass:

| Checkpoint | What Is Checked |
| --- | --- |
| Code review | Another developer reads the code before it merges |
| Functional test | Feature works as described in the task |
| Edge case test | Handles bad input, empty data, and slow connections |
| Mobile test | Works correctly on a phone — critical for the Kenya market |
| Payment test | M-Pesa and gateway flows tested with real sandbox transactions |
| Security check | No exposed data, no unauthorised access possible |
| Client UAT | Client uses the system as a real member would |

# 12. What the Client Owns

At every phase, these decisions belong to the client:

What goes into each phase — priorities can be adjusted at any time

Design approval — nothing goes live that the client has not seen

Content — text, images, property data, community information

Member communications — what gets sent to members and when

Go or No-Go on every production launch

Admin user creation — who gets which admin role

# 13. Summary

Organize → Design → Build → Test → Ship

This cycle repeats for all four phases, tightening each time as the team becomes more familiar with the codebase and the client becomes more confident reviewing builds.

Phase 1 is next. It begins with Sprint 1: database schema, authentication, and member registration.